## RICs
Cause	Effect	Impact	Response	Custodian	Dates
					Identification	Occurrence	Closure
Difficult to assign role	Late for choosing role	Medium	choose the roles based on their own personal skill	Owner and Scrum Manager	22.1.2024	22.1.2024	Close
Error when connecting to database and intellij	Late for committing querys in Github	High	create meeting for that error and try to figure out the solution	Developers	29.1.2024	30.1.2024	Close
Found an error when commit the unit test to the Github	Late to make unit testing	Medium	Check the code again and try to figure out the solution	All Teams	6.2.2024	7.2.2024	Close